## PRODUCT BACKLOG
Moravian Womens Basketball Practice Statistics Application
PRODUCT BACKLOG
User Story ID | User Story | Estimate (size) | Priority | Sprint | Task owner | Estimated effort
US001 | The client will need a means to create and modify a team roster. |  | 5 | 1
US002 | The client needs to track number of free throws made and attempted on a daily basis. |  | 4
US003 | The client needs to track the number of three point shot attempts and number made on a daily basis. |  | 4
US004 | The client wants to be able to have displayed summary statistical information on free thows and three-point shots (like percentages made). |  | 4
US005 | The client would like to see the summary data on free throws and three-point shots as a chart that show trends. |  | 4
US006 | The client would like to see the summary statistics and charts from a given date to present. |  | 4
US007 | The client would like to be able to see historical data on a specific player. This will include data from each year the player has been on the team |  | 2
USOO8 | The client wants to track specific data on players such as player number, player name, year played, free throw statistics, three-point shot statistics |  | 1
US009 | The user may want to track where the three-point attempts were attempted at (center, left elbow, right elbow, left corner, right corner) |  | 1
US010 | Client wants system to be installed and usable on their local laptop |  | 5 | 2
US011 | Client want font size to be bigger. |  | 5 | 2
US012 | Client wants to be able to sort the roster by player name or player number. |  | 5 | 2
US013 | Client wants the player data to be store by some means so that it is persistent, up to date, and modifiable |  | 5 | 2
US014 | Client wants the roster to contain the current players on the team. |  | 5 | 2
US015 | Client want to have the ability to track data for free throws and three point shots multiple times in the same day |  | 3
Note on D7: stakeholdermap.com: Whatever method you are using for estimation. It could be story points, Fibonacci scale or T-shirt sizes - small, medium, large.
Note on E7: stakeholdermap.com: To change the Priority menu click on the DROPDOWN MENUS worksheet.
Note on F7: stakeholdermap.com: To change the Priority menu click on the DROPDOWN MENUS worksheet.
Note on G7: stakeholdermap.com: An optional field for the person responsible for the completion of the User Story.
Note on H7: stakeholdermap.com: This is an optional field for estimated effort in hours or days.

## PROJECT DETAILS
PROJECT NUMBER
PROJECT NAME
PROJECT MANAGER
DATE
VERSION

## DROPDOWN MENUS
PRIORITY | SPRINT
1 | 1
2 | 2
3 | 3
4 | 4
5 | 5
6
7
8
9
10
TO EDIT THE DROPDOWN MENUS
Click on the Data tab. Under Data Tools, select Data Validation. Under Settings change the Source to match the values you want to appear in the menu.
TO DELETE THE DROPDOWN MENUS
Click on the Data tab. Under Data Tools, select Data Validation. Under Settings change the Allow to Any value.

## RESOURCES
Useful resources
Burndown Chart Template
Daily Scrum Meeting Template
Project Management Templates
The Top 50 Business Risks (and how to manage them)!
Issue Log Template [free download]
End Project Report Template
Risk Register Template
Stakeholder Management Templates
Work Breakdown Structure (WBS) template in Excel