## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | SPRINT REVIEW
User Story #1 |  |  |  |  | Tuesday 2/13 | Thursday 2/15 | Tuesday 2/ 20 | Thursday 2/22 | Tuesday 2/27 | Thursday 2/29 | Tuesday 3/5
Create simple GUI - tabbed panes (going to create a web app as well prep for next sprint) |  | Brandon / Nate | Done | 8 | 8 | 8 | 4 | 4 | 0 | 0 | 0
One pane will be for modifying the team roster |  | Brandon / Nate | Done | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
Add players to the roster |  | Austin/Saul | Done | 16 | 16 | 12 | 8 | 2 | 1 | 0 | 0
Implementing a lister object that sends new player info to the model |  | Austin | Done | 12 | 6 | 5 | 4 | 3 | 2 | 1 | 0
Display player info as a roster |  | Brandon / Nate | Done | 8 | 8 | 7 | 5 | 3 | 1 | 0 | 0
Storing player information in a database |  | Saul/Austin | Done | 12 | 12 | 7 | 3 | 0 | 0 | 0 | 0
User Story #2 |  |  |  |  | Thursday 3/7 | Tuesday 3/12 | Thursday 3/14 | Tuesday 3/19 | Thursday 3/21 | Tuesday 3/26 | Thursday 3/28
Create the system to be installed and usable on their local laptop |  | Brandon |  | 20 | 20 | 20 | 16 | 14 | 14 | 14 | 14
Make font size to be bigger. |  | Brandon/Nathan | Done | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Make the player data to be store by some means such as the year so that it is persistent, up to date, and modifiable |  | Austin/Saul | Done | 24 | 24 | 20 | 14 | 10 | 8 | 4 | 0
Get our SpringBoot web app working |  | Austin/Saul/Brandon/Nathan |  | 40 | 35 | 30 | 27 | 27 | 27 | 27 | 24
Refactor code to have the ability to track data for free throws and three point shots multiple times in the same day or different days |  | Austin/Saul | Done | 18 | 15 | 12 | 7 | 6 | 2 | 0 | 0
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 163 | 149 | 126 | 93 | 74 | 56 |  |  | 0