## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | SPRINT REVIEW
User Story #1 |  |  |  |  | Tuesday 2/13 | Thursday 2/15 | Tuesday 2/ 20 | Thursday 2/22 | Tuesday 2/27 | Thursday 2/29 | Tuesday 3/5
Create simple GUI - tabbed panes (going to create a web app as well prep for next sprint) |  | Brandon / Nate | Done | 8 | 8 | 8 | 4 | 4 | 0 | 0 | 0
One pane will be for modifying the team roster |  | Brandon / Nate | Done | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
Add players to the roster |  | Austin/Saul | Done | 16 | 16 | 12 | 8 | 2 | 1 | 0 | 0
Implementing a lister object that sends new player info to the model |  | Austin | Done | 12 | 6 | 5 | 4 | 3 | 2 | 1 | 0
Display player info as a roster |  | Brandon / Nate | Done | 8 | 8 | 7 | 5 | 3 | 1 | 0 | 0
Storing player information in a database |  | Saul/Austin | Done | 12 | 12 | 7 | 3 | 0 | 0 | 0 | 0
User Story #2
Client wants system to be installed and usable on their local laptop
Client want font size to be bigger.
Client wants the player data to be store by some means such as the year so that it is persistent, up to date, and modifiable
Client want to have the ability to track data for free throws and three point shots multiple times in the same day
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL